## PLAN
Section | Task Name | Requirements | Status | Notes | Start | Finish | Predecessors | Notes | Progress | Item owner | Customer (S) | Links | In place / needed | Source of evidence
| Solace Game Engine |  |  |  | 2025-01-29
1.4 | Engine Library | C++, X64
1.4 | Level Editor | C#, WPF
1.4 | Dynamic Link Library (DLL)
Communication between Engine Lib & Level Editor
1.4 | Game Code | C++
Scripts to be attached to game objects
1.4 | Engine Library

## VIDEOS
Part | Task Header | Task Name | Duration (sec) | Duration | Finish | Notes | Progress | Item owner | Links | Rounded
| Video Tutorial | [7 empty] | https://www.youtube.com/@GameEngineSeries
Game Engine Programming
1 | Game Engine Programming 001 | Introduction | 2129 | 35m29s | 2025-01-29 |  | Complete |  |  | 35
2 | Game Engine Programming 002 | Loading project templates for game projects | 2953 | 49m13s | 2025-01-31 |  | Complete |  |  | 49
3 | Game Engine Programming 003 | Implement creating new game projects | 2963 | 49m23s | 2025-02-01 |  | Complete |  |  | 49
4 | Game Engine Programming 004 | Loading game projects | 2912 | 48m32s | 2025-02-02 |  | Complete |  |  | 49
5 | Game Engine Programming 005 | Add/remove scenes and undo-redo system | 3132 | 52m12s | 2025-02-03 |  | Complete |  |  | 52
6 | Game Engine Programming 006 | Implement game entity and components in Primal editor | 3087 | 51m27s | 2025-02-05 |  | Complete |  |  | 51
7 | Game Engine Programming 007 | Undoable selections and a message log | 3903 | 65m03s | 2025-02-08 |  | Complete |  |  | 65
8 | Game Engine Programming 008 | Multiselection game entities | 3569 | 59m29s | 2025-02-10 |  | Complete |  |  | 59
9 | Game Engine Programming 009 | Identifiers with index and generation parts | 4283 | 71m23s | 2025-02-12 |  | Complete |  |  | 71
10 | Game Engine Programming 010 | Entity and component implementation in C++ | 3301 | 55m01s | 2025-02-14 |  | Complete |  |  | 55
11 | Game Engine Programming 011 | Testing entities system and creating the engine DLL | 4997 | 83m17s | 2025-02-17 |  | Complete |  |  | 83
12 | Game Engine Programming 012 | Dark UI theme and animations | 3242 | 54m02s | 2025-02-19 |  | Complete |  |  | 54
13 | Concept art 20200831 |  | 301 | 05m01s |  |  | Complete |  |  | 5
14 | Game Engine Programming 013 | Finishing the dark UI theme | 2503 | 41m43s | 2025-02-26 |  | Complete |  |  | 42
15 | Game Engine Programming 014 | NumberBox, ScalarBox, VectorBox | 2934 | 48m54s | 2025-03-04 |  | Complete |  |  | 49
16 | Game Engine Programming 015 | Transform component | 3481 | 58m01s |  |  | In Progress |  |  | 58
17 | Game Engine Programming 016 | C++ scripting and script component | 3430 | 57m10s |  |  | Not Started |  |  | 57
18 | Game Engine Programming 017 | Generating the Visual Studio solution for game code | 2787 | 46m27s |  |  | Not Started |  |  | 46
19 | Game Engine Programming 018 | Adding source files using Visual Studio automation | 3553 | 59m13s |  |  | Not Started |  |  | 59
20 | Space ship concept art 201017 |  | 198 | 03m18s |  |  | Not Started |  |  | 3
21 | Game Engine Programming 019 | Building and loading the game code DLL | 3390 | 56m30s |  |  | Not Started |  |  | 57
22 | Game Engine Programming 020.1 | Loading functions from game code DLL explicitly | 1177 | 19m37s |  |  | Not Started |  |  | 20
23 | Game Engine Programming 020.2 | Script component | 1450 | 24m10s |  |  | Not Started |  |  | 24
24 | Game Engine Programming 020.3 | Finishing the script component | 1062 | 17m42s |  |  | Not Started |  |  | 18
25 | Game Engine Programming 021.1 | Save the game project in binary format | 1450 | 24m10s |  |  | Not Started |  |  | 24
26 | Game Engine Programming 021.2 | Read the game project from binary file | 1193 | 19m53s |  |  | Not Started |  |  | 20
27 | Game Engine Programming 021.3 | Running the stand-alone game | 799 | 13m19s |  |  | Not Started |  |  | 13
28 | Making of conept art 201126 |  | 503 | 08m23s |  |  | Not Started |  |  | 8
29 | Game Engine Programming 022.1 | Opening a game window... | 1685 | 28m05s |  |  | Not Started |  |  | 28
30 | Game Engine Programming 022.2 | Continue opening a game window... | 1535 | 25m35s |  |  | Not Started |  |  | 26
31 | Game Engine Programming 022.3 | Testing windows | 1167 | 19m27s |  |  | Not Started |  |  | 19
32 | Game Engine Programming 022.4 | Open a window for the game application | 882 | 14m42s |  |  | Not Started |  |  | 15
33 | Game Engine Programming 023.1 | Hosting a Win32 window in WPF | 1372 | 22m52s |  |  | Not Started |  |  | 23
34 | Game Engine Programming 023.2 | Handling resize for hosted windows | 1059 | 17m39s |  |  | Not Started |  |  | 18
35 | Game Engine Programming 023.3 | Finish hosting Win32 windows in WPF | 945 | 15m45s |  |  | Not Started |  |  | 16
36 | Game Engine Programming 024.1 | Setting up the geometry pipeline | 1476 | 24m36s |  |  | Not Started |  |  | 25
37 | Game Engine Programming 024.2 | Generating a plane grid procedurally | 1180 | 19m40s |  |  | Not Started |  |  | 20
38 | Game Engine Programming 024.3 | Processing vertex normals | 1629 | 27m09s |  |  | Not Started |  |  | 27
39 | Game Engine Programming 024.4 | Processing vertex UVs and packing for GPU | 1112 | 18m32s |  |  | Not Started |  |  | 19
40 | Game Engine Programming 025.1 | Writing geometry data to a memory buffer | 1393 | 23m13s |  |  | Not Started |  |  | 23
41 | Game Engine Programming 025.2 | The geometry asset class | 1025 | 17m05s |  |  | Not Started |  |  | 17
42 | Game Engine Programming 025.3 | Reading data into the geometry asset class | 931 | 15m31s |  |  | Not Started |  |  | 16
43 | Game Engine Programming 026.1 | Primitive mesh dialog window | 1826 | 30m26s |  |  | Not Started |  |  | 30
44 | Game Engine Programming 026.2 | WPF 3D mesh renderer viewmodel | 1744 | 29m04s |  |  | Not Started |  |  | 29
45 | Game Engine Programming 026.3 | WPF 3D mesh renderer view | 1277 | 21m17s |  |  | Not Started |  |  | 21
46 | Game Engine Programming 026.4 | Camera movement for the WPF 3D mesh renderer | 1386 | 23m06s |  |  | Not Started |  |  | 23
47 | Game Engine Programming 027.1 | Procedurally generated UV Sphere | 1906 | 31m46s |  |  | Not Started |  |  | 32
48 | Game Engine Programming 027.2 | UV mapping the UV Sphere | 1363 | 22m43s |  |  | Not Started |  |  | 23
49 | Game Engine Programming 028.1 | Saving geometry to asset file | 1684 | 28m04s |  |  | Not Started |  |  | 28
50 | Game Engine Programming 028.2 | Generating icons for asset files | 953 | 15m53s |  |  | Not Started |  |  | 16
51 | Game Engine Programming 029.1 | Setting up graphics rendering | 1424 | 23m44s |  |  | Not Started |  |  | 24
52 | Game Engine Programming 029.2 | Initializing DirectX 12 | 1981 | 33m01s |  |  | Not Started |  |  | 33
53 | Game Engine Programming 030.1 | GPU work submission | 1127 | 18m47s |  |  | Not Started |  |  | 19
54 | Game Engine Programming 030.2 | Synchronizing CPU and GPU | 983 | 16m23s |  |  | Not Started |  |  | 16
55 | Game Engine Programming 031.1 | Descriptor heap allocator | 1514 | 25m14s |  |  | Not Started |  |  | 25
56 | Game Engine Programming 031.2 | Finishing descriptor heap allocator | 1083 | 18m03s |  |  | Not Started |  |  | 18
57 | Game Engine Programming 032.1 | DirectX (DXGI) Swap Chain | 1441 | 24m01s |  |  | Not Started |  |  | 24
58 | Game Engine Programming 032.2 | Using the render surface | 1341 | 22m21s |  |  | Not Started |  |  | 22
59 | Game Engine Programming 033.1 | Free-list and vector containers | 1414 | 23m34s |  |  | Not Started |  |  | 24
60 | Game Engine Programming 033.2 | Use the free-list with utl::vector and std::vector | 1204 | 20m04s |  |  | Not Started |  |  | 20
61 | Game Engine Programming 034.1 | A texture class for the Direct3D 12 render engine | 1647 | 27m27s |  |  | Not Started |  |  | 27
62 | Game Engine Programming 034.2 | The render texture and depth buffer class | 821 | 13m41s |  |  | Not Started |  |  | 14
63 | Game Engine Programming 035.1 | DirectX 12 pipelines and the root signature | 1260 | 21m00s |  |  | Not Started |  |  | 21
64 | Game Engine Programming 035.2 | DirectX 12 root signature and pipeline helpers | 1793 | 29m53s |  |  | Not Started |  |  | 30
65 | Game Engine Programming 036.1 | SFINAE | 1102 | 18m22s |  |  | Not Started |  |  | 18
66 | Game Engine Programming 036.2 | Infrastructure for engine shaders | 1605 | 26m45s |  |  | Not Started |  |  | 27
67 | Game Engine Programming 036.3 | Compiling HLSL shaders with DXC | 1650 | 27m30s |  |  | Not Started |  |  | 28
68 | Game Engine Programming 037.1 | Introduction to Forward+ rendering -geometry pass | 1760 | 29m20s |  |  | Not Started |  |  | 29
69 | Game Engine Programming 037.2 | Resource states and barriers | 1446 | 24m06s |  |  | Not Started |  |  | 24
70 | Game Engine Programming 038.1 | Post-process submodule | 2131 | 35m31s |  |  | Not Started |  |  | 36
71 | Game Engine Programming 038.2 | Resizing swap chain's back-buffers | 1798 | 29m58s |  |  | Not Started |  |  | 30
72 | Game Engine Programming | Announcing Primal+ | 354 | 05m54s |  |  | Not Started |  |  | 6
73 | Game Engine Programming 039 | Switching projects + Visual Studio automation | 1951 | 32m31s |  |  | Not Started |  |  | 33
74 | Game Engine Programming 040.1 | The asset registry | 1554 | 25m54s |  |  | Not Started |  |  | 26
75 | Game Engine Programming 040.2 | The Content Browser | 1407 | 23m27s |  |  | Not Started |  |  | 23
76 | Game Engine Programming 040.3 | Styling The Content Browser | 1415 | 23m35s |  |  | Not Started |  |  | 24
77 | Game Engine Programming 040.4 | Content Browser Tile View | 1006 | 16m46s |  |  | Not Started |  |  | 17
78 | Game Engine Programming 041.1 | Improving Content Browser 's Architecture | 1248 | 20m48s |  |  | Not Started |  |  | 21
79 | Game Engine Programming 041.2 | Save File Dialog | 1121 | 18m41s |  |  | Not Started |  |  | 19
80 | Game Engine Programming 042.1 | Using FBX SDK to import 3D scenes | 1200 | 20m00s |  |  | Not Started |  |  | 20
81 | Game Engine Programming 042.2 | Getting vertex data and LODs from FBX files | 1345 | 22m25s |  |  | Not Started |  |  | 22
82 | Game Engine Programming 043.1 | Dropping files onto content browser for import | 1322 | 22m02s |  |  | Not Started |  |  | 22
83 | Game Engine Programming 043.2 | Viewing imported geometry | 1600 | 26m40s |  |  | Not Started |  |  | 27
84 | Game Engine Programming 044.1 | Improving FBX scene import | 1363 | 22m43s |  |  | Not Started |  |  | 23
85 | Game Engine Programming 044.2 | Geometry detail view | 761 | 12m41s |  |  | Not Started |  |  | 13
86 | Game Engine Programming 044.3 | Packing vertex elements | 1149 | 19m09s |  |  | Not Started |  |  | 19
87 | Game Engine Programming 044.4 | Finishing vertex packing | 1104 | 18m24s |  |  | Not Started |  |  | 18
88 | Game Engine Programming 045.1 | Using a copy command queue to upload data to GPU | 1561 | 26m01s |  |  | Not Started |  |  | 26
89 | Game Engine Programming 045.2 | Upload context | 1496 | 24m56s |  |  | Not Started |  |  | 25
90 | Game Engine Programming 046.1 | Geometry hierarchy | 1515 | 25m15s |  |  | Not Started |  |  | 25
91 | Game Engine Programming 046.2 | Sending geometry to GPU | 1778 | 29m38s |  |  | Not Started |  |  | 30
92 | Game Engine Programming 047.1 | Camera | 1635 | 27m15s |  |  | Not Started |  |  | 27
93 | Game Engine Programming 047.2 | Mathematics of view and projection matrices | 2049 | 34m09s |  |  | Not Started |  |  | 34
94 | Game Engine Programming 047.3 | Rotations and quaternions | 1454 | 24m14s |  |  | Not Started |  |  | 24
95 | Game Engine Programming 048.1 | Render items | 1148 | 19m08s |  |  | Not Started |  |  | 19
96 | Game Engine Programming 048.2 | Material shaders | 1376 | 22m56s |  |  | Not Started |  |  | 23
97 | Game Engine Programming 048.3 | Upgrade to Visual Studio 2022 & Primal+ stuff | 1233 | 20m33s |  |  | Not Started |  |  | 21
98 | Game Engine Programming 049.1 | Introducing low-level materials | 1313 | 21m53s |  |  | Not Started |  |  | 22
99 | Game Engine Programming 049.2 | Finishing low-level materials | 1099 | 18m19s |  |  | Not Started |  |  | 18
100 | Game Engine Programming 050.1 | Low-level render items | 1626 | 27m06s |  |  | Not Started |  |  | 27
101 | Game Engine Programming 050.2 | Gpass and depth pre-pass pipeline state objects | 1554 | 25m54s |  |  | Not Started |  |  | 26
102 | Game Engine Programming 051.1 | Constant buffer | 1044 | 17m24s |  |  | Not Started |  |  | 17
103 | Game Engine Programming 051.2 | HLSL/C++ shared types + GPass cache | 1151 | 19m11s |  |  | Not Started |  |  | 19
104 | Game Engine Programming 051.3 | Depth-prepass and render functions | 964 | 16m04s |  |  | Not Started |  |  | 16
105 | Game Engine Programming 051.4 | First render! | 1231 | 20m31s |  |  | Not Started |  |  | 21
106 | Game Engine Programming 052.1 | Updating entity transform components | 1223 | 20m23s |  |  | Not Started |  |  | 20
107 | Explaining my game engine in 2020 | Part1 | 899 | 14m59s |  |  | Not Started |  |  | 15
108 | Game Engine Programming 052.2 | Fixing the graphics and reversing depth | 1449 | 24m09s |  |  | Not Started |  |  | 24
109 | Explaining my game engine in 2020 | Part2: Multi-selection and data-oriented game entities | 912 | 15m12s |  |  | Not Started |  |  | 15
110 | Game Engine Programming 052.3 | Compiling HLSL shader variations | 1356 | 22m36s |  |  | Not Started |  |  | 23
111 | Explaining my game engine in 2020 | Part3: UI colors, entity scripts and game code DLL | 916 | 15m16s |  |  | Not Started |  |  | 15
112 | Game Engine Programming 053.1 | Directional lights | 1318 | 21m58s |  |  | Not Started |  |  | 22
113 | Game Engine Programming 053.2 | Directional lights part 2 | 1135 | 18m55s |  |  | Not Started |  |  | 19
114 | Game Engine Programming 054.1 | Sending light data to GPU | 955 | 15m55s |  |  | Not Started |  |  | 16
115 | Game Engine Programming 054.2 | Forward Shading | 1097 | 18m17s |  |  | Not Started |  |  | 18
116 | Game Engine Programming 054.3 | Creating a scene to test the lighting | 1091 | 18m11s |  |  | Not Started |  |  | 18
117 | Game Engine Programming 055.1 | Basic input handling | 1441 | 24m01s |  |  | Not Started |  |  | 24
118 | Explaining my game engine in 2020 | Part1: The geometry pipeline | 718 | 11m58s |  |  | Not Started |  |  | 12
119 | Game Engine Programming 055.2 | Using input to move around the scene | 1183 | 19m43s |  |  | Not Started |  |  | 20
120 | Explaining my game engine in 2020 | Part2: Spheres (mostly) | 648 | 10m48s |  |  | Not Started |  |  | 11
121 | Game Engine Programming 055.3 | Input binding | 1127 | 18m47s |  |  | Not Started |  |  | 19
122 | Explaining my game engine in 2020 | Part3: GPU work submission and root signatures | 834 | 13m54s |  |  | Not Started |  |  | 14
123 | Game Engine Programming 056.1 | Tightly packed light arrays | 1216 | 20m16s |  |  | Not Started |  |  | 20
124 | Game Engine Programming 056.2 | Adding and removing point lights and spotlights | 1131 | 18m51s |  |  | Not Started |  |  | 19
125 | Game Engine Programming 056.3 | Sending point light and spotlight data to GPU | 1184 | 19m44s |  |  | Not Started |  |  | 20
126 | Explaining my game engine in 2020 | Part4: Shaders, Foreward+ architecture, resource barriers | 550 | 09m10s |  |  | Not Started |  |  | 9
127 | Game Engine Programming 057.1 | Tile-based light culling: grid frustums | 1498 | 24m58s |  |  | Not Started |  |  | 25
128 | Game Engine Programming 057.2 | Tile-based light culling: dispatch compute shader | 1201 | 20m01s |  |  | Not Started |  |  | 20
129 | Game Engine Programming 057.3 | Tile-based light culling: Visualizing grid frustums | 1151 | 19m11s |  |  | Not Started |  |  | 19
130 | Explaining my game engine in 2020 | Part5: Full-screen triangle, complex numbers, fractals | 656 | 10m56s |  |  | Not Started |  |  | 11
131 | Game Engine Programming 058.1 | Tile-based light culling compute shader | 1039 | 17m19s |  |  | Not Started |  |  | 17
132 | Game Engine Programming 058.2 | Tile-based light culling: Intersection testing | 1033 | 17m13s |  |  | Not Started |  |  | 17
133 | Game Engine Programming 058.3 | Tile-based light culling: Dispatch culling shader | 1407 | 23m27s |  |  | Not Started |  |  | 23
134 | Game Engine Programming 058.4 | Tile-based light culling: Forward+ lighting | 1511 | 25m11s |  |  | Not Started |  |  | 25
135 | Explaining my game engine in 2022 | Part1: Dealing with FBX scene hierarchies | 586 | 09m46s |  |  | Not Started |  |  | 10
136 | Game Engine Programming 059.1 | Optimizing Forward+: Cleaning up the lighting code | 1530 | 25m30s |  |  | Not Started |  |  | 26
137 | Game Engine Programming 059.2 | Optimizing Forward+: using bounding spheres | 1434 | 23m54s |  |  | Not Started |  |  | 24
138 | Game Engine Programming 059.3 | Optimizing Forward+: approximate sphere-cone intersection | 1870 | 31m10s |  |  | Not Started |  |  | 31
139 | Explaining my game engine in 2022 | Part2: Upload resources, camera projection types | 601 | 10m01s |  |  | Not Started |  |  | 10
140 | Game Engine Programming 059.4 | HLSL wave intrinsics and dealing with depth discontinuities | 1526 | 25m26s |  |  | Not Started |  |  | 25
141 | Game Engine Programming 059.5 | Finish forward+ optimization | 868 | 14m28s |  |  | Not Started |  |  | 14
142 | Explaining my game engine in 2022 | Part3: View and projection transformations | 1056 | 17m36s |  |  | Not Started |  |  | 18
143 | Game Engine Programming 060.1 | Reading and decoding image files with DirectXTex | 1761 | 29m21s |  |  | Not Started |  |  | 29
144 | Game Engine Programming 060.2 | Initialize scratch image and generate mipmaps | 1070 | 17m50s |  |  | Not Started |  |  | 18
145 | Explaining my game engine in 2022 | Part4: Rotations and quaternions | 813 | 13m33s |  |  | Not Started |  |  | 14
146 | Game Engine Programming 060.3 | Explaining block compression formats and sRGB color space | 1006 | 16m46s |  |  | Not Started |  |  | 17
147 | Game Engine Programming 060.4 | Compressing textures with DirectXTex library | 1182 | 19m42s |  |  | Not Started |  |  | 20
148 | Game Engine Programming 060.5 | Normal map identification, decompress texture | 1274 | 21m14s |  |  | Not Started |  |  | 21
149 | Explaining my game engine in 2022 | Part5: Render items, materials, caching, reverse depth buffer | 809 | 13m29s |  |  | Not Started |  |  | 13
150 | Game Engine Programming 061.1 | Texture asset class | 1406 | 23m26s |  |  | Not Started |  |  | 23
151 | Game Engine Programming 061.2 | Texture import and thumbnail generation | 1163 | 19m23s |  |  | Not Started |  |  | 19
152 | Game Engine Programming 061.3 | Use C# P/Invoke to call C++ texture importer | 1150 | 19m10s |  |  | Not Started |  |  | 19
153 | Game Engine Programming 062.1 | Saving/loading imported textures & opening Texture Editor window | 1249 | 20m49s |  |  | Not Started |  |  | 21
154 | Game Engine Programming 062.2 | Display image and pan and zoom in Texture Editor window | 1215 | 20m15s |  |  | Not Started |  |  | 20
155 | Game Engine Programming 062.3 | Viewing block compression textures and mip levels | 1119 | 18m39s |  |  | Not Started |  |  | 19
156 | Game Engine Programming 063.1 | Enhancing Texture Editor | 1286 | 21m26s |  |  | Not Started |  |  | 21
157 | Explaining my game engine in 2023 | Part1: Introduction to Phong lighting | 679 | 11m19s |  |  | Not Started |  |  | 11
158 | Game Engine Programming 063.2 | Selecting RGBA channels using a WPF shader effect | 1176 | 19m36s |  |  | Not Started |  |  | 20
159 | Game Engine Programming 063.3 | Viewing imported texture details | 1325 | 22m05s |  |  | Not Started |  |  | 22
160 | Explaining my game engine in 2023 | Part2: Input devices, tightly packed light buffers | 484 | 08m04s |  |  | Not Started |  |  | 8
161 | Game Engine Programming 064.1 | Cleaning up and improving the texture code | 1750 | 29m10s |  |  | Not Started |  |  | 29
162 | Game Engine Programming 064.2 | Creating new folders and renaming files and folders | 1198 | 19m58s |  |  | Not Started |  |  | 20
163 | Game Engine Programming 064.3 | Content browser import options | 868 | 14m28s |  |  | Not Started |  |  | 14
164 | Explaining my game engine in 2023 | Part3: Tile-based light culling, compute shaders, RenderDoc | 666 | 11m06s |  |  | Not Started |  |  | 11
165 | Game Engine Programming 065.1 | Import settings configuration and asset proxies | 1748 | 29m08s |  |  | Not Started |  |  | 29
166 | Game Engine Programming 065.2 | Geometry import settings configuration | 1797 | 29m57s |  |  | Not Started |  |  | 30
167 | Game Engine Programming 066.1 | More geometry import settings configuration | 1067 | 17m47s |  |  | Not Started |  |  | 18
168 | Game Engine Programming 066.2 | Folder selection dialog | 883 | 14m43s |  |  | Not Started |  |  | 15
169 | Explaining my game engine in 2023 | Part4: Foreward+ light buffers, intersection testing | 492 | 08m12s |  |  | Not Started |  |  | 8
170 | Game Engine Programming 066.3 | Display statistics for importing assets | 1403 | 23m23s |  |  | Not Started |  |  | 23
171 | Game Engine Programming 066.4 | Import progression and coalescing meshes | 1491 | 24m51s |  |  | Not Started |  |  | 25
172 | Explaining my game engine in 2023 | Part5: Light Culling with Approximate Sphere-Cone Intersection | 475 | 07m55s |  |  | Not Started |  |  | 8
173 | Game Engine Programming 067.1 | Texture import settings configuration | 1053 | 17m33s |  |  | Not Started |  |  | 18
174 | Game Engine Programming 067.2 | More texture import settings configuration | 1368 | 22m48s |  |  | Not Started |  |  | 23
175 | Game Engine Programming 067.3 | Adding texture import settings controls | 1233 | 20m33s |  |  | Not Started |  |  | 21
176 | Game Engine Programming 067.4 | Re-importing textures | 571 | 09m31s |  |  | Not Started |  |  | 10
177 | Explaining my game engine in 2023 | Part6: HLSL waves + texture import pipeline | 499 | 08m19s |  |  | Not Started |  |  | 8
178 | Game Engine Programming 068.1 | Uploading textures to GPU | 1598 | 26m38s |  |  | Not Started |  |  | 27
179 | Game Engine Programming 068.2 | Test texture upload | 1341 | 22m21s |  |  | Not Started |  |  | 22
180 | Game Engine Programming 069.1 | Prepare the pixel shader for texture sampling | 1348 | 22m28s |  |  | Not Started |  |  | 22
181 | Game Engine Programming 069.2 | Texturing with bindless resources | 1300 | 21m40s |  |  | Not Started |  |  | 22
182 | Explaining my game engine in 2023 | Part7: Block Compression texture formats, sRGB color space | 946 | 15m46s |  |  | Not Started |  |  | 16
183 | Game Engine Programming 070.1 | Constructing a tangent space for triangle meshes | 1267 | 21m07s |  |  | Not Started |  |  | 21
184 | Game Engine Programming 070.2 | Texturing with normal maps in HLSL | 770 | 12m50s |  |  | Not Started |  |  | 13
185 | Game Engine Programming 070.3 | Mikk TSpace | 1222 | 20m22s |  |  | Not Started |  |  | 20
186 | Game Engine Programming 071.1 | Introduction to Physically Based Rendering | 740 | 12m20s |  |  | Not Started |  |  | 12
187 | Game Engine Programming 071.2 | Adding PBR material properties and the geometry component | 1138 | 18m58s |  |  | Not Started |  |  | 19
188 | Explaining my game engine in 2024 | Part1: Triangle mesh tangent space, normal map identification | 607 | 10m07s |  |  | Not Started |  |  | 10
189 | Evolution of Primal Engine 2024: | Thank you for 10.000 Subs! | 284 | 04m44s |  |  | Not Started |  |  | 5
190 | Game Engine Programming 071.3 | Finish implementation of PBR | 1511 | 25m11s |  |  | Not Started |  |  | 25
191 | Game Engine Programming 072.1 | Converting equirectangular HDR images to cube maps using the CPU | 1288 | 21m28s |  |  | Not Started |  |  | 21
192 | Game Engine Programming 072.2 | Using the GPU to Convert equirectangular images to cube maps | 1158 | 19m18s |  |  | Not Started |  |  | 19
193 | Game Engine Programming 072.3 | Viewing cube maps in the editor | 872 | 14m32s |  |  | Not Started |  |  | 15
194 | Game Engine Programming 073.1 | Sampling methods for pre-filtering diffuse Image Based Lighting | 942 | 15m42s |  |  | Not Started |  |  | 16
195 | Game Engine Programming 073.2 | Using compute shaders for pre-filtering diffuse Image Based Lighting | 1305 | 21m45s |  |  | Not Started |  |  | 22
196 | Game Engine Programming 073.3 | Editor support for pre-filtered IBL cube maps | 1176 | 19m36s |  |  | Not Started |  |  | 20
197 | Game Engine Programming 074.1 | Brief introduction to importance sampling | 661 | 11m01s |  |  | Not Started |  |  | 11
198 | Game Engine Programming 074.2 | Importance sampling Cook-Torrance BRDF + the split sum approximation | 1045 | 17m25s |  |  | Not Started |  |  | 17
199 | Game Engine Programming 074.3 | Implementing specular BRDF pre-filtering for IBL | 825 | 13m45s |  |  | Not Started |  |  | 14
200 | Game Engine Programming 075.1 | Image based lighting | 1447 | 24m07s |  |  | Not Started |  |  | 24
|  |  | 280734 | 398 881 sec |  | Progress: | 768 |  |  | 4677
|  |  | 4679 | 6648 min 1 sec
|  |  | 78 hr | 110 hr 48 min

## KEYS
Red | Must Watch
Green | Recommended
Blue | Skippable